## Entry Criteria for SIT&RFS
Criteria | Owner | Status | Target Date | Actual Completion Date | Comments
Requirements / User Stories finalized | Business Analyst / Product Owner | Not Started | 3 Week before Test Execution date
BRSD / Functional Specification signed off | Business Analyst / Business Stakeholders | Not Started | 3 Week before Test Execution date
Scope finalized and approved | Project Manager / Product Owner | Not Started | 3 Week before Test Execution date
Test planning and estimation completed | QA Lead | Not Started | 1 Week before Test Execution date
Test plan signed off | QA Lead / Project Manager | Not Started | 1 Week before Test Execution date
SIT/RFS test scenarios and test cases prepared | QA Team | Not Started | 1 Week before Test Execution date
SIT/RFS test scenarios and test cases reviewed and signed off | QA Lead / Business Analyst / Development Team | Not Started | 4 Days before Test Execution date
Requirement Traceability Matrix prepared | QA Team | Not Started | 1 Week before Test Execution date
Test data prepared and validated | QA Team / Business Team | Not Started | 1 Week before Test Execution date
SIT/RFS environment setup completed | Environment Team / Development Team | Not Started | 3 Days before Test Execution date
Required interfaces / integrations available | Development Team / Integration Team | Not Started | 1 Week before Test Execution date
Build deployed successfully in SIT environment | Development Team / Release Team | Not Started | 2 Days before Test Execution date
Smoke testing completed successfully | QA Team | Not Started | 2 Days before Test Execution date
Defect management process agreed | QA Lead / Project Manager | Not Started | 1 Week before Test Execution date
Azure updated with latest stories and test cases | QA Team / Scrum Master | Not Started | 1 Week before Test Execution date
Required access provided to QA team | System Admin / Environment Team | Not Started | 3 Days before Test Execution date
Test execution dependencies identified and resolved | QA Lead / Project Manager | Not Started | 1 Week before Test Execution date
No blocker issue preventing SIT execution | QA Lead / Project Manager | Not Started | 1 Day before Test Execution date
SIT entry sign-off received | QA Lead / Project Manager / Business Stakeholders | Not Started | 1 Day before Test Execution date

## Exit Criteria for SIT&RFS
Criteria | Owner | Status | Target Date | Actual Completion Date | Comments
SIT execution completed for all planned scope | QA Lead | Not Started | 1 Week before the target date
All critical business flows tested | QA Lead | Not Started | 1 Week before the target date
Regression testing completed | QA Lead | Not Started | 1 Week before the target date
All high and critical defects fixed and retested | QA Lead | Not Started | 3 Days before the target date
No open blocker or critical defects | QA Lead | Not Started | 3 Days before the target date
Medium defects reviewed and accepted by stakeholders | QA Lead | Not Started | 3 Days before the target date
Test summary report completed | QA Lead | Not Started | 2 Days before the target date
Defect leakage and RCA reviewed | QA Lead/Business Team/ Business Analyst | Not Started | 2 Days before the target date
Requirement Traceability Matrix updated | QA Lead | Not Started | 2 Days before the target date
SIT sign-off provided by QA | QA Lead | Not Started | 2 Days before the target date
Build approved for UAT / next phase | QA Lead | Not Started | 2 Days before the target date

## Entry Criteria for UAT
Criteria | Owner | Status | Target Date | Actual Completion Date | Comments
SIT completed successfully | QA Team | Not Started | 4 Days before the target date
SIT sign-off received | QA Lead / Project Manager / Business Stakeholders | Not Started | 2 Days before the target date
No open blocker or critical defects from SIT | QA Lead | Not Started | 2 Days before the target date
UAT scope finalized and approved | QA Lead / Business Teams | Not Started | 2 Week before the target date
UAT scenarios and business flows prepared | QA Team | Not Started | 1 Week before the target date
UAT scenarios reviewed and signed off | QA Lead / Business Teams | Not Started | 1 Week before the target date
UAT environment setup completed | Environment Team / Development Team | Not Started | 1 Week before the target date
UAT test data prepared | QA Team | Not Started | 4 Days before the target date
Production-like data validated if applicable | QA Team | Not Started | 4 Days before the target date
Business users identified and trained | Project Manager / Business Teams | Not Started | 2–3 Week before the target date
Access provided to business users | System Admin / QA Team | Not Started | 1 Week before the target date
UAT defect process communicated | QA Lead | Not Started | 1 Week before the target date
Azure DevOps updated with latest UAT scenarios | QA Lead / Scrum Master | Not Started | 1 Week before the target date
Required integrations and interfaces available | Development Team / Integration Team | Not Started | 1 Week before the target date
Required business reports and dashboards available | Development Team / Business Team | Not Started | 4 Days before the target date
Build deployed successfully in UAT environment | QA Lead / Development Team | Not Started | 3 Days before the target date
Smoke testing completed in UAT environment | QA Team | Not Started | 2 Days before the target date
No blocker issue preventing UAT execution | QA Lead / Project Manager | Not Started | 1 Day before the target date
Formal UAT entry sign-off received | QA Lead / Project Manager / Business Stakeholders | Not Started | 1 Day before the target date

## Exit Criteria for UAT
Criteria | Owner | Status | Target Date | Actual Completion Date | Comments
UAT execution completed for all planned scenarios | QA Lead/Business Team | Not Started | 1 Week before the target date
All business-critical scenarios passed | QA Lead/Business Team | Not Started | 1 Week before the target date
Business users validated end-to-end flows | QA Lead/Business Team | Not Started | 1 Week before the target date
All blocker and critical defects closed | QA Lead/Business Team | Not Started | 4 Days before the target date
High severity defects resolved or accepted with workaround | QA Team/Business Team/ Business Analyst/Development Team | Not Started | 3 Days before the target date
Medium and low severity defects reviewed and accepted | QA Team/Business Team/ Business Analyst/Development Team | Not Started | 3 Days before the target date
Retesting completed for resolved defects | Business Team | Not Started | 4 Days before the target date
No open issues preventing go-live | QA Lead/Business Team | Not Started | 2 Days before the target date
Test summary report completed | QA Lead | Not Started | 2 Days before the target date
Business sign-off provided | Business Team | Not Started | 2 Days before the target date
Deployment / release approval received | QA Lead/Development Lead/Project Manager | Not Started | 2 Days before the target date
Go-live readiness confirmed | QA Lead | Not Started | 2 Days before the target date
Defect summary and RCA completed | QA Lead | Not Started | 2 Days before the target date
Requirement Traceability Matrix updated | QA Lead | Not Started | 2 Days before the target date