## Sheet1
Defect ID | Title | Module | Description | Test Phase | Severity | Priority | Status | TC ID Linked | Steps to Reproduce | Expected Result | Actual Result | Assigned To | Reported By | Reported Date | Retest Status | Comments | Screenshot Link
DEF-001 | Lead Conversion Fails and Creates Duplicate Account Records | Lead Management | When converting a lead with an existing email address, the system creates a duplicate account instead of linking to the existing customer account. | UAT | Critical | High | Open | TC-LEAD-015 | 1. Login to CRM application 2. Search for an existing customer account with email abc@test.com 3. Create a new lead using the same email address 4. Convert the lead into Account and Contact | System should identify the existing account and link the converted lead to the existing customer record without duplication | System creates a new duplicate account record and an additional contact, causing duplicate customer data in CRM | CRM Dev Team | QA Team | 2026-04-19 | Pending | This impacts reporting, customer history, and downstream integrations with sales and support modules | Screenshot_DEF_001.png