## RCA Template
RCA ID | Defect ID | Project Name | Module / Feature | Reported By | Reported Date | Severity | Priority | Defect Summary | Business Impact | Root Cause Category | Root Cause Description | Why 1 | Why 2 | Why 3 | Why 4 | Why 5 | Corrective Action | Preventive Action | Owner | Target Resolution Date | Actual Resolution Date | Status | Lessons Learned
RCA-001 | DEF-010 | Salesforce CPQ Release 1.0 | Quote Approval Workflow | QA Team | 19-Apr-2026 | Critical | High | Approval workflow did not trigger for discounts above 20% | Quotes bypassed approval causing financial risk | Requirement Gap | Discount threshold was documented incorrectly in the requirement document | Requirement stated 25% instead of 20% | Business team did not review requirement | QA tested based on incorrect requirement | No validation checklist existed | Requirement sign-off process was incomplete | Updated approval threshold and redeployed build | Add business review checklist for approval rules | Business Analyst / Development Team | 22-Apr-2026 | 21-Apr-2026 | Closed | Business review should be mandatory for approval workflows
RCA-002 | DEF-021 | Salesforce CRM Release 2.0 | Lead Conversion | QA Team | 20-Apr-2026 | Critical | High | Duplicate account created during lead conversion | Duplicate customer records impacted reporting | Development Issue | Existing account matching logic was missing in code | Code did not check existing email address | Developer assumed unique lead data | Requirement lacked duplicate validation rule | Test data did not cover duplicate scenarios | Peer review missed the logic gap | Added duplicate validation logic | Include duplicate scenarios in test coverage | Development Team | 23-Apr-2026 | 22-Apr-2026 | Closed | Negative scenarios should be covered in unit and QA testing
RCA-003 | DEF-030 | Salesforce CPQ Release 1.0 | Quote PDF Generation | Business User | 21-Apr-2026 | Medium | Medium | Tax amount displayed incorrectly on quote PDF | Incorrect customer-facing quote values | Data Issue | Tax mapping field was pulling incorrect value from backend | Wrong field mapping configured | Configuration review was incomplete | Business logic not documented clearly | No test case existed for tax validation | Regression scope missed PDF validation | Updated field mapping configuration | Add PDF validation scenarios in regression suite | QA Team / Development Team | 24-Apr-2026 | 24-Apr-2026 | Closed | Customer-facing documents require dedicated validation
RCA-004 | DEF-041 | Salesforce Service Cloud Release | Case Attachment | QA Team | 22-Apr-2026 | High | Medium | Users unable to open attachments from closed cases | Support team unable to access historical customer records | Environment Issue | Attachment service URL was different in SIT environment | Incorrect environment configuration | Environment refresh missed attachment settings | No validation done after refresh | Smoke test did not cover attachment access | Dependency checklist was incomplete | Corrected attachment service URL | Add environment validation checklist after refresh | Environment Team | 25-Apr-2026 | 24-Apr-2026 | Closed | Environment validation should be part of smoke testing
RCA-005 | DEF-050 | Salesforce CPQ Release 2.0 | Bundled Product Pricing | QA Team | 23-Apr-2026 | High | High | Incorrect pricing calculated for bundled products | Revenue and quote accuracy impacted | Integration Issue | Pricing API returned outdated pricing rules | Old pricing rules were cached | Integration refresh failed | No alert configured for stale pricing data | Regression did not include bundled product pricing | Monitoring process was missing | Cleared cache and refreshed pricing API | Add API monitoring and pricing validation scenarios | Integration Team / Development Team | 26-Apr-2026 | 25-Apr-2026 | Closed | Pricing-related integrations require continuous monitoring